## Risk Register
Risk ID | Asset ID | Asset Name | Business Function | Risk Category | Threat | Vulnerability / Weakness | Risk Scenario | Existing Controls | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Risk Rating | Risk Treatment | Treatment Action | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Rating | Status | Risk Acceptance | Notes
RISK-001 | AST-005 | Active Directory | IT Operations | Identity & Access Management | Credential compromise | Privileged accounts do not consistently require MFA | An attacker compromises privileged credentials and gains unauthorized access to multiple critical systems | Password authentication; RBAC; SIEM monitoring | 4 | 5 |  |  | Mitigate | Implement MFA for all privileged accounts and monitor authentication exceptions | IT Security Manager | 2026-11-07 | 2 | 5 |  |  | Open | Not Accepted | High-value identity infrastructure
RISK-002 | AST-001 | Core Banking System | Banking | Unauthorized Access | Account compromise | Excessive privilege or compromised administrator credentials | Unauthorized user obtains elevated access to the core banking platform and accesses or alters customer transactions | RBAC; MFA; SIEM; vulnerability management | 3 | 5 |  |  | Mitigate | Review privileged access quarterly and enforce strong authentication | Head of Core Banking | 2026-12-07 | 2 | 5 |  |  | Open | Not Accepted | Critical banking service
RISK-003 | AST-002 | Online Banking Platform | Digital Banking | Application Security | Web application attack | Unpatched or exploitable application vulnerability | An attacker exploits a vulnerability in the public-facing banking portal to gain unauthorized access or disrupt service | WAF; MFA; SIEM; vulnerability scanning | 3 | 5 |  |  | Mitigate | Perform regular application security testing and prioritize critical vulnerabilities | Head of Digital Banking | 2026-11-22 | 2 | 5 |  |  | Open | Not Accepted | Internet-facing critical service
RISK-004 | AST-003 | Mobile Banking Application | Digital Banking | Application Security | Mobile application compromise | Application vulnerability or insecure API | An attacker exploits an application or API weakness to access customer information or initiate unauthorized activity | MFA; secure SDLC; SIEM; vulnerability management | 3 | 5 |  |  | Mitigate | Conduct mobile/API penetration testing and remediate high-risk findings | Head of Digital Banking | 2026-12-07 | 2 | 5 |  |  | Open | Not Accepted | Customer-facing application
RISK-005 | AST-004 | Payment Processing System | Payments | Operational Resilience | Payment service disruption | Failure of critical payment component or external dependency | A technical failure or attack disrupts payment processing and prevents customers from completing transactions | Network segmentation; SIEM; DR capability | 3 | 5 |  |  | Mitigate | Test payment failover and third-party continuity arrangements | Head of Payments | 2026-11-30 | 2 | 5 |  |  | Open | Not Accepted | Critical payment service
RISK-006 | AST-006 | SIEM Platform | Security Operations | Security Monitoring | Loss of security visibility | SIEM outage or incomplete log ingestion | Security events are not collected or analyzed, delaying detection and response to cyber incidents | Log monitoring; alerting; redundancy | 3 | 4 |  |  | Mitigate | Implement health monitoring for log sources and SIEM service availability | SOC Manager | 2026-12-15 | 2 | 4 |  |  | Open | Not Accepted | Security monitoring dependency
RISK-007 | AST-007 | EDR Platform | Security Operations | Endpoint Security | Malware / ransomware | Endpoint telemetry or protection unavailable | Malware executes on employee endpoints without timely detection or containment | EDR; SIEM; disk encryption | 3 | 4 |  |  | Mitigate | Monitor EDR coverage and investigate unmanaged endpoints | SOC Manager | 2026-11-30 | 2 | 4 |  |  | Open | Not Accepted | Endpoint protection
RISK-008 | AST-008 | Vulnerability Management Platform | Vulnerability Management | Patch Management | Missed vulnerability remediation | Incomplete asset coverage or stale vulnerability data | Critical vulnerabilities remain unaddressed because scanning or remediation tracking is incomplete | Vulnerability scanning; reporting | 3 | 4 |  |  | Mitigate | Reconcile vulnerability scans against the asset inventory and track overdue remediation | Security Manager | 2026-11-22 | 2 | 4 |  |  | Open | Not Accepted | Supports vulnerability governance
RISK-009 | AST-009 | Firewall Infrastructure | Network Security | Network Security | Network intrusion | Misconfiguration or ineffective filtering | An attacker bypasses or exploits network security controls to reach internal systems | Firewall rules; network segmentation; IDS/IPS; SIEM | 3 | 5 |  |  | Mitigate | Perform periodic firewall rule review and network security testing | Network Security Manager | 2026-12-15 | 2 | 5 |  |  | Open | Not Accepted | Critical network boundary
RISK-010 | AST-010 | Backup Infrastructure | Resilience | Business Continuity | Data loss / ransomware | Backups unavailable, corrupted or accessible to attackers | A major cyber incident prevents recovery because critical backups are unavailable or compromised | Encryption; access control; immutable backups; monitoring | 3 | 5 |  |  | Mitigate | Conduct quarterly restore tests and verify immutable backup coverage | IT Operations Manager | 2026-11-30 | 2 | 5 |  |  | Open | Not Accepted | Critical recovery capability
RISK-011 | AST-011 | CRM Platform | Customer Management | Third-Party ICT Risk | Cloud/SaaS compromise | Weak supplier security controls or service disruption | A compromise or outage at the CRM provider exposes customer information or disrupts customer operations | MFA; RBAC; logging; supplier assessment | 3 | 4 |  |  | Mitigate | Perform formal ICT supplier assessment and review contractual security requirements | Customer Operations Manager | 2026-12-31 | 2 | 4 |  |  | Open | Not Accepted | Third-party dependency
RISK-012 | AST-012 | Corporate Email | Corporate Communication | Phishing | Phishing / Business Email Compromise | User credentials or sessions compromised through social engineering | An attacker compromises an employee mailbox and uses it to access information or conduct fraudulent activity | MFA; anti-phishing; EDR; email security | 4 | 4 |  |  | Mitigate | Strengthen phishing-resistant MFA and conduct targeted awareness testing | IT Operations Manager | 2026-12-15 | 2 | 4 |  |  | Open | Not Accepted | High-volume attack vector
RISK-013 | AST-013 | Employee Laptops | Workforce | Endpoint Security | Lost or stolen device | Sensitive information exposed on endpoint | Loss or theft of an employee device exposes business information or enables unauthorized access | EDR; disk encryption; MFA; MDM | 3 | 3 |  |  | Mitigate | Verify encryption and MDM coverage across all managed endpoints | IT Operations Manager | 2026-11-30 | 2 | 3 |  |  | Open | Not Accepted | Endpoint fleet
RISK-014 | AST-014 | Database Infrastructure | Data Management | Data Protection | Data breach | Unauthorized database access | An attacker or unauthorized insider obtains access to sensitive banking and transaction data | Encryption; RBAC; MFA; backup; SIEM | 3 | 5 |  |  | Mitigate | Review database privileged access and implement enhanced monitoring for sensitive queries | Database Manager | 2026-12-15 | 2 | 5 |  |  | Open | Not Accepted | Restricted banking data
RISK-015 | AST-015 | Network Infrastructure | IT Operations | Operational Resilience | Network outage | Hardware failure, configuration error or denial-of-service | Network disruption prevents access to critical banking and security services | Network monitoring; configuration backup; segmentation | 3 | 5 |  |  | Mitigate | Test network redundancy and maintain current configurations and recovery procedures | Network Manager | 2026-12-31 | 2 | 5 |  |  | Open | Not Accepted | Critical shared dependency

## Scoring Matrix
Risk Score | Rating | Interpretation
1 | Low | Limited risk; routine controls generally sufficient
2 | Low | Limited risk; routine controls generally sufficient
3 | Low | Limited risk; routine controls generally sufficient
4 | Low | Limited risk; routine controls generally sufficient
5 | Medium | Requires management attention
6 | Medium | Requires management attention
7 | Medium | Requires management attention
8 | Medium | Requires management attention
9 | Medium | Requires management attention
10 | High | Significant risk requiring treatment
11 | High | Significant risk requiring treatment
12 | High | Significant risk requiring treatment
13 | High | Significant risk requiring treatment
14 | High | Significant risk requiring treatment
15 | High | Significant risk requiring treatment
16 | High | Significant risk requiring treatment
17 | Critical | Severe risk requiring urgent treatment
18 | Critical | Severe risk requiring urgent treatment
19 | Critical | Severe risk requiring urgent treatment
20 | Critical | Severe risk requiring urgent treatment
21 | Critical | Severe risk requiring urgent treatment
22 | Critical | Severe risk requiring urgent treatment
23 | Critical | Severe risk requiring urgent treatment
24 | Critical | Severe risk requiring urgent treatment
25 | Critical | Severe risk requiring urgent treatment
5×5 Likelihood × Impact Matrix
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25

## Risk Reference
Risk Category | Definition
Identity & Access Management | Risks related to authentication, authorization and privileged access
Unauthorized Access | Unauthorized access to systems, accounts or data
Application Security | Vulnerabilities or attacks affecting applications and APIs
Operational Resilience | Disruption of critical technology or business services
Security Monitoring | Loss or degradation of detection and monitoring capability
Endpoint Security | Compromise, loss or inadequate protection of endpoints
Patch Management | Failure to identify or remediate vulnerabilities
Network Security | Network intrusion, misconfiguration or connectivity failure
Business Continuity | Failure to recover critical services or data
Third-Party ICT Risk | Risks arising from ICT suppliers and dependencies
Phishing | Social engineering, credential theft and business email compromise
Data Protection | Unauthorized disclosure, modification or loss of sensitive data