## Summary
BalticTrust Bank — Remediation Tracker Summary
Metric | Value | Purpose
Total actions |  | All example actions in the tracker
Critical priority |  | Review immediately and validate urgency
High priority |  | Plan timely remediation
Not started |  | Actions not yet underway
In progress |  | Actions underway
Blocked |  | Resolve dependency or escalation
Overdue |  | Check target dates and escalate
Due soon |  | Review actions due within 14 days
Closed |  | Close only after evidence review

## Read Me
BalticTrust Bank — Remediation Tracker
Purpose | Track corrective actions arising from the illustrative GRC gap assessment and audit findings register.
Workbook sheets | Summary: action counts and schedule health. Remediation Tracker: action details, owner, priority, progress, due dates, blockers, evidence, and closure review.
How to use | Validate each action against your findings. Update owner, supporting team, target date, status, and percentage complete. Add evidence links or references that do not expose secrets or personal data.
Schedule health | Calculated from the target date and current date: Overdue means target date has passed; Due soon means target date is within 14 days; On track means more than 14 days remain; Closed follows status. Confirm formula behavior in your spreadsheet application.
Status definitions | Not Started = no work begun; In Progress = work underway; Blocked = a dependency prevents progress; Ready for Review = action is reported complete and awaiting validation; Closed = closure evidence reviewed; Accepted Risk = formally approved risk acceptance.
Closure criteria | Do not close an action merely because work is reported complete. Record objective evidence, have the designated reviewer assess it, and document the closure date.
Portfolio disclaimer | BalticTrust Bank is fictional. Actions, owners, dates, and priorities are illustrative examples and are not evidence of actual remediation. Adapt them to the validated findings and approved risk method.
Suggested workflow | Audit finding → corrective action → owner and due date → evidence collection → reviewer validation → closure or further action.

## Remediation Tracker
Action ID | Linked Finding ID | Action Title | Related Domain | Priority | Root Cause / Gap Addressed | Remediation Task | Success Criteria | Accountable Owner | Supporting Team | Date Raised | Target Date | Status | % Complete | Days Until Due | Schedule Health | Dependency / Blocker | Evidence Link / Reference | Closure Reviewer | Closure Date | Notes
ACT-001 | AF-001 | Formalize cybersecurity risk governance | Governance | High | Management review cadence and evidence expectations may not be assigned. | Create a quarterly ICT/cyber risk review pack, meeting agenda, decision log, and action tracker. | A review is held, decisions and owners are recorded, and overdue actions are followed up. | Risk & Compliance Lead | Security; IT Operations | 2026-10-09 | 2027-01-15 | Not Started | 0% |  |  | Agree governance forum and attendees. | Simulated evidence: meeting pack and action log | GRC Reviewer |  | Illustrative action; validate scope and owners.
ACT-002 | AF-002 | Reconcile asset inventory | Asset Management | High | Inventory ownership, criticality, lifecycle, or dependencies may be incomplete. | Review asset records with service owners; assign owner, criticality, lifecycle status, and service dependency fields. | All in-scope critical assets have an owner and criticality; reconciliation exceptions are tracked. | IT Operations Manager | Application owners; Infrastructure | 2026-10-09 | 2026-12-20 | Not Started | 0% |  |  | Obtain current inventory and owner confirmations. | Updated asset inventory; reconciliation log | IT Risk Reviewer |  | Cross-reference 02-Asset-Inventory.
ACT-003 | AF-003 | Standardize risk treatment approvals | Risk Management | High | Risk treatment and residual-risk approval trail may be inconsistent. | Document scoring criteria and treatment options; record risk owner, action, due date, residual risk, and approval. | Risk register entries contain documented treatment decisions and authorized residual-risk approvals. | ICT Risk Manager | GRC; control owners | 2026-10-09 | 2026-12-22 | Not Started | 0% |  |  | Agree risk appetite and approval authority. | Updated risk register; treatment approvals | GRC Reviewer |  | Cross-reference 03-Risk-Assessment.
ACT-004 | AF-004 | Verify privileged access and MFA | Identity & Access | Critical | MFA coverage and access review evidence need verification. | Review privileged and remote access; verify MFA coverage; remove unnecessary access; document time-limited exceptions. | MFA coverage is evidenced for defined in-scope access; access review exceptions have owners and approvals. | IAM Administrator | Security; IT Operations | 2026-10-09 | 2027-01-12 | Not Started | 0% |  |  | Access to identity configuration and group listings. | MFA report; access review sign-off; exception log | Security Reviewer |  | Use simulated evidence only in public portfolio.
ACT-005 | AF-005 | Improve vulnerability remediation tracking | Vulnerability Management | High | Risk-based patch timelines and exception handling may be inconsistent. | Define remediation SLAs by severity; link authorized scan results to tickets; report overdue findings and exceptions. | Findings have a severity, owner, target date, status, and verified closure evidence. | Security Engineer | IT Operations; Change Management | 2026-10-09 | 2027-01-25 | Not Started | 0% |  |  | Agree remediation SLAs and change windows. | Sample scan report; patch report; remediation tickets | Security Reviewer |  | Use authorized testing and non-sensitive sample data.
ACT-006 | AF-006 | Exercise incident response workflow | Incident Management | High | Incident roles, escalation, exercise schedule, and reporting decision criteria may be unclear. | Approve severity matrix and response procedure; run a tabletop exercise; record lessons and corrective actions. | Exercise completed; lessons assigned to owners; reporting decision process documented and reviewed. | Incident Response Lead | Compliance; IT; Communications | 2026-10-09 | 2027-01-25 | Not Started | 0% |  |  | Confirm participant availability and scenario. | Approved procedure; tabletop report; action log | GRC Reviewer |  | Validate regulatory requirements against current official sources.
ACT-007 | AF-007 | Test backup restoration and recovery | Business Continuity & Recovery | High | Recovery objectives and restoration test evidence may be incomplete. | Define recovery objectives for critical services; perform a controlled restore test; document results and lessons. | Restore tests record expected versus actual recovery and have follow-up actions for exceptions. | Business Continuity Manager | IT Operations; Service owners | 2026-10-09 | 2027-02-15 | Not Started | 0% |  |  | Agree test scope and change window. | Recovery plan; restore-test report; action log | Business Continuity Reviewer |  | Coordinate testing to avoid unintended service disruption.
ACT-008 | AF-008 | Review critical ICT suppliers | Third-Party ICT Risk | High | Supplier tiering, due diligence, contract review, and exit planning may need improvement. | Identify critical suppliers; complete risk-tiered due diligence; review relevant contract clauses and exit options. | Critical suppliers have current assessments, documented decisions, and tracked contractual or exit-plan gaps. | Third-Party Risk Manager | Procurement; Legal; IT | 2026-10-09 | 2027-02-10 | Not Started | 0% |  |  | Obtain supplier register and relevant contracts. | Supplier register; due diligence; contract review | Third-Party Risk Reviewer |  | Validate legal and contract-specific obligations.
ACT-009 | AF-009 | Validate framework mapping traceability | GRC / Compliance | Medium | Mapping review and approval process may not be formally defined. | Review internal control-to-framework references, applicability, evidence, and exceptions; record reviewer and date. | Mappings have documented validation status, evidence references, and accountable reviewers. | GRC Analyst | Security; Compliance | 2026-10-09 | 2027-02-28 | Not Started | 0% |  |  | Confirm authoritative framework versions and internal control IDs. | Reviewed mappings; validation log; evidence index | GRC Lead |  | Mapping does not establish certification or compliance.
ACT-010 | AF-010 | Establish closure review process | Assurance & Improvement | Medium | Finding closure criteria and independent review may not be consistently established. | Use one central findings/action tracker; define escalation and closure criteria; require evidence review before closure. | Each action has one accountable owner, due date, status, and documented closure review. | GRC Analyst / Internal Audit | Control owners; Management | 2026-10-09 | 2027-02-28 | Not Started | 0% |  |  | Agree central tracker owner and closure authority. | Remediation tracker; closure evidence; reviewer sign-off | GRC Lead |  | Use with 08-GRC-Gap-Assessment and 09-Audit-Findings-Register.
Formulas:
Days Until Due = IF([Target Date]="","",[Target Date]-TODAY())
Schedule Health = IF([Status]="Closed","Closed",IF([Target Date]="","No target date",IF([Target Date]<TODAY(),"Overdue",IF([Target Date]-TODAY()<=14,"Due soon","On track"))))