## Summary
BalticTrust Bank — Audit Findings Summary
Metric | Value | Interpretation
Total illustrative findings |  | Example findings; validate before reporting
Critical findings |  | Prioritize immediate review
High findings |  | Plan timely corrective action
Medium findings |  | Schedule proportionate remediation
Low findings |  | Monitor in line with risk appetite
Open findings |  | Awaiting remediation
In progress |  | Remediation underway
Closed |  | Closure requires reviewed evidence

## Read Me
BalticTrust Bank — Audit Findings Register
Purpose | Track illustrative audit findings, root causes, risk ratings, corrective actions, owners, due dates, status, and closure evidence.
Workbook sheets | Summary: counts by severity and status. Audit Findings: detailed register. Risk Score = Likelihood × Impact.
How to use | Validate each finding against evidence. Edit the finding description, criteria, root cause, risk scores, recommendation, owner, and target date to fit your assessment.
Status definitions | Open = not started; In Progress = remediation underway; Blocked = impediment exists; Ready for Review = action reportedly complete; Closed = evidence reviewed and finding closure validated; Accepted Risk = formally accepted by authorized role.
Risk scoring | Likelihood and impact are each rated 1–5. Risk Score is their product. Treat the supplied severity as a starting assessment and update it according to your approved scoring criteria.
Evidence discipline | A finding should reference objective evidence, not assumptions alone. For the fictional portfolio, clearly label simulated evidence and avoid including secrets or real personal data.
Scope and disclaimer | BalticTrust Bank is fictional. This workbook is for educational portfolio purposes only; it is not a formal audit, legal opinion, or proof of compliance. Findings are illustrative and must be validated before being described as actual results.
Recommended practice | Assign one accountable owner per corrective action, set realistic deadlines, escalate overdue high-risk findings, and require a reviewer to verify closure evidence.

## Audit Findings
Finding ID | Finding Title | Audit Area | Finding Description | Criteria / Reference | Root Cause (Initial) | Risk / Impact | Severity | Likelihood (1-5) | Impact (1-5) | Risk Score | Recommendation | Corrective Action | Finding Owner | Date Identified | Target Date | Status | Closure Evidence | Reviewer / Validator | Notes
AF-001 | Cybersecurity governance review evidence | Governance | Periodic management review of cybersecurity and ICT risk should be evidenced through a defined cadence, decisions, and tracked actions. | Internal governance procedure; relevant NIST CSF 2.0 Govern outcomes; applicable DORA governance provisions | Review cadence and evidence expectations may not be formally assigned. | Management may lack timely visibility of material cybersecurity risks and overdue decisions. | High | 3 | 5 |  | Establish a regular risk governance review with documented decisions and action tracking. | Create a quarterly reporting pack, meeting agenda, minutes template, and action log. | Risk & Compliance Lead | 2026-10-09 | 2027-01-15 | Open | Risk committee minutes; dashboard; action log | GRC Reviewer | Illustrative portfolio finding; validate against evidence before presenting as an actual audit finding.
AF-002 | Asset inventory ownership and criticality | Asset Management | Asset records may not consistently include an accountable owner, business criticality, lifecycle status, and service dependencies. | Asset management procedure; ISO 27001 mapping; NIST CSF 2.0 ID.AM outcomes; applicable DORA Article 8 themes | Inventory fields and reconciliation responsibilities may be incomplete. | Incomplete asset visibility can weaken risk assessment, patch prioritization, and recovery planning. | High | 4 | 4 |  | Maintain a reconciled inventory with ownership, classification, criticality, and dependencies. | Review inventory fields with service owners and establish a periodic reconciliation process. | IT Operations Manager | 2026-10-09 | 2026-12-20 | Open | Updated asset inventory; reconciliation record | IT Risk Reviewer | Cross-reference 02-Asset-Inventory.
AF-003 | Risk treatment and acceptance trail | Risk Management | Risk treatment decisions and residual-risk approvals should be consistently documented and traceable to risk owners. | Risk management methodology; risk register; applicable ISO 27001 and DORA themes | Approval and evidence requirements may not be consistently defined. | Risks could remain untreated without explicit, accountable acceptance. | High | 4 | 5 |  | Record treatment decisions, accountable owners, due dates, residual risk, and approvals. | Update the risk register and establish a documented risk acceptance workflow. | ICT Risk Manager | 2026-10-09 | 2026-12-22 | Open | Updated risk register; treatment plan; approvals | GRC Reviewer | Cross-reference 03-Risk-Assessment.
AF-004 | Privileged access and MFA verification | Identity & Access | Evidence is needed to demonstrate MFA coverage for privileged/remote access and periodic review of access rights. | Access control policy; ISO 27001 mapping; NIST CSF 2.0 PR.AA outcomes | Access review cadence and evidence collection may not be assigned to a specific role. | Unauthorized or excessive access may increase risk of account compromise and misuse. | Critical | 4 | 5 |  | Verify MFA coverage and establish regular access reviews with documented exception approval. | Generate coverage report, review privileged groups, resolve excess access, and track exceptions. | IAM Administrator | 2026-10-09 | 2027-01-12 | Open | MFA coverage report; access review sign-off; exception log | Security Reviewer | Illustrative priority; validate with actual configuration evidence.
AF-005 | Vulnerability and patch remediation tracking | Vulnerability Management | A consistent process should track vulnerability findings, risk-based remediation deadlines, exceptions, and closure evidence. | Vulnerability management standard; NIST CSF 2.0 ID.RA / PR.PS themes; applicable DORA themes | Patch timelines and exception handling may not be uniformly defined. | Known vulnerabilities may remain exposed beyond acceptable risk tolerances. | High | 4 | 4 |  | Define remediation timelines by severity and monitor overdue findings and approved exceptions. | Create a remediation tracker linked to authorized scan results and change records. | Security Engineer | 2026-10-09 | 2027-01-25 | Open | Scan reports; patch report; tickets; exception approvals | Security Reviewer | Use authorized testing and fictional/sample evidence in a public portfolio.
AF-006 | Incident response exercise and reporting workflow | Incident Management | Incident roles, classification, escalation, exercise evidence, and applicable reporting decision criteria should be documented. | Incident response procedure; NIST CSF 2.0 Respond outcomes; DORA incident-related provisions as applicable | Exercise schedule and reporting responsibilities may not be clearly allocated. | Delayed escalation or inconsistent handling could increase incident impact and reporting risk. | High | 3 | 5 |  | Approve incident response procedures and test them through a tabletop exercise. | Create severity matrix, reporting decision flow, contact-role list, and exercise action log. | Incident Response Lead / Compliance Officer | 2026-10-09 | 2027-01-25 | Open | Approved procedure; tabletop report; action log | GRC Reviewer | Validate regulatory applicability and reporting deadlines against current official requirements.
AF-007 | Backup restoration and recovery test evidence | Business Continuity & Recovery | Recovery plans should identify priorities and objectives, and backup restoration should be tested with results and follow-up actions recorded. | BCP/DR procedures; NIST CSF 2.0 Recover outcomes; applicable DORA Article 11/12 themes | Testing ownership and evidence retention may not be defined. | Failure to restore systems within expected times could disrupt critical services. | High | 3 | 5 |  | Define recovery objectives for critical services and conduct documented restoration tests. | Schedule restore tests, record actual results against objectives, and track corrective actions. | Business Continuity Manager | 2026-10-09 | 2027-02-15 | Open | Recovery plan; restore-test report; remediation evidence | Business Continuity Reviewer | Cross-reference planned BCP/DR portfolio stage.
AF-008 | ICT supplier due diligence and exit planning | Third-Party ICT Risk | Supplier criticality, due diligence, periodic review, contractual protections, and exit planning should be evidenced for relevant ICT suppliers. | Supplier risk procedure; NIST CSF 2.0 GV.SC themes; applicable DORA Articles 28 and 30 themes | Supplier tiering and reassessment requirements may not be fully operationalized. | Supplier failure or concentration risk could affect service continuity and control effectiveness. | High | 4 | 5 |  | Use risk-tiered due diligence and monitoring; document relevant contractual and exit arrangements. | Create supplier inventory, review critical supplier files, and track gaps to closure. | Third-Party Risk Manager | 2026-10-09 | 2027-02-10 | Open | Supplier register; due diligence; contract review; exit plan | Third-Party Risk Reviewer | Legal and contract-specific requirements need validation.
AF-009 | Framework mapping traceability and validation | GRC / Compliance | Control mappings should retain traceability from internal control IDs to framework references, evidence, applicability, and approved exceptions. | ISO 27001 mapping; NIST CSF 2.0 mapping; DORA mapping; internal GRC method | Mapping review and approval process may not be defined. | Unvalidated mappings may create inaccurate compliance claims or missed obligations. | Medium | 3 | 4 |  | Review mappings for accuracy, applicability, and evidence; record reviewer and date. | Add validation fields and conduct a documented review of each framework mapping. | GRC Analyst | 2026-10-09 | 2027-02-28 | Open | Reviewed mappings; validation log; evidence index | GRC Lead | Mapping is not equivalent to certification or legal compliance.
AF-010 | Central remediation tracking and closure review | Assurance & Improvement | Findings and corrective actions should be maintained in a single tracker with accountable owners, due dates, and independent closure review. | GRC gap assessment; internal audit procedure; applicable framework improvement outcomes | Closure criteria and reviewer independence may not be explicitly established. | Actions may be overdue or marked closed without sufficient evidence of effectiveness. | Medium | 3 | 4 |  | Create a central action tracker and require evidence review before closure. | Assign action owners, escalation rules, status updates, and closure validation responsibilities. | GRC Analyst / Internal Audit | 2026-10-09 | 2027-02-28 | Open | Remediation tracker; closure evidence; reviewer sign-off | GRC Lead | Use this register with the GRC-Gap-Assessment workbook.