## Summary
BalticTrust Bank — BCP / Disaster Recovery Summary
Metric | Value | Interpretation
Critical services |  | Illustrative service list
Critical-rated services |  | Confirm through business impact analysis
Services not yet tested |  | Plan and document recovery tests
Recovery scenarios |  | Example recovery scenarios
Draft recovery plans |  | Review and approve before operational use

## Read Me
BalticTrust Bank — BCP / DR Plan
Purpose | Provide an educational template for business continuity and disaster recovery planning for a fictional financial institution.
Workbook sheets | Summary: high-level counts. Critical Services: business services, dependencies, impact, criticality, MTD/RTO/RPO, strategy, and testing. Recovery Plan: scenario activation, recovery sequence, communications, dependencies, and return-to-normal criteria.
RTO and RPO | RTO (Recovery Time Objective) is the target time to restore a service. RPO (Recovery Point Objective) is the target maximum data-loss window measured in time. MTD is the maximum tolerable downtime. These objectives require business approval and feasibility review.
How to use | Validate service inventory and dependencies; perform a business impact analysis; approve RTO/RPO; assign recovery roles; document actual test results and follow-up actions.
Test discipline | A plan marked Draft is not operationally approved. Conduct controlled tests, record outcomes, protect production services, and close lessons learned.
Security | Do not put passwords, recovery keys, internal phone lists, real supplier confidential information, or sensitive infrastructure details in a public repository.
Portfolio disclaimer | BalticTrust Bank and the service details are fictional. All objectives, roles, and strategies are illustrative; they do not demonstrate actual recovery capability or regulatory compliance.

## Critical Services
Service ID | Critical Business Service | Business Process | Service Owner | Supporting Systems / Dependencies | Impact if Unavailable | Criticality | Maximum Tolerable Downtime (MTD) | Recovery Time Objective (RTO) | Recovery Point Objective (RPO) | Recovery Strategy | Backup / Replication Approach | Recovery Priority | Test Frequency | Last Test Date | Next Test Date | Test Status | Open Recovery Actions | Notes
SVC-001 | Online banking | Customer account access and transactions | Head of Digital Banking | Identity provider; core banking platform; network; databases; cloud/hosting; payment interfaces | Customers may be unable to view balances or initiate transactions; operational and reputational impact. | Critical | 24 hours | 4 hours | 15 minutes | Recover core services in approved alternate environment; validate dependencies before business resumption. | Encrypted backups and database replication; access and restore procedures documented. | 1 — Highest | At least annually and after material changes |  |  | Not Tested | Define and test recovery runbook. | Illustrative fictional service; confirm objectives through business impact analysis.
SVC-002 | Card payment processing | Authorization and settlement support | Head of Payments | Payment switch; card processor; network; HSM; identity/access; supplier connections | Card transactions may be declined or delayed; customer and merchant impact. | Critical | 8 hours | 2 hours | 5 minutes | Fail over to approved resilient processing capability; reconcile queued transactions after recovery. | Replication and transaction recovery procedures; supplier continuity arrangements. | 2 — High | At least annually and after material changes |  |  | Not Tested | Confirm processor dependencies and reconciliation steps. | Illustrative only; supplier capabilities and contractual terms must be validated.
SVC-003 | Customer support contact centre | Customer enquiries and incident communications | Customer Operations Manager | Telephony; CRM; workforce access; knowledge base; network | Customers may be unable to obtain timely support or incident updates. | High | 48 hours | 12 hours | 4 hours | Redirect calls to alternate capacity; provide approved status messaging and manual procedures. | Application backups; configuration export; alternate communication arrangements. | 3 — Medium | Annually |  |  | Not Tested | Document alternate staffing and communications plan. | Illustrative objectives require business approval.
SVC-004 | Internal identity and access management | Staff authentication and authorization | IT Operations Manager | Directory; MFA; privileged access tools; DNS; network; endpoint management | Staff may be unable to access business systems; emergency access may be constrained. | Critical | 12 hours | 4 hours | 1 hour | Use documented identity recovery procedures and controlled emergency access with logging. | Protected configuration backups; recovery accounts; tested restoration procedures. | 1 — Highest | At least annually and after material changes |  |  | Not Tested | Review break-glass access controls and recovery dependencies. | Keep actual credentials and sensitive configuration out of this workbook and public repository.
SVC-005 | Regulatory and risk reporting | Risk, compliance, and management reporting | Chief Risk Officer | GRC platform; data warehouse; reporting tools; document repository | Delayed reporting, reduced oversight, and potential missed obligations. | High | 72 hours | 24 hours | 4 hours | Restore reporting platform and prioritize legally or operationally time-sensitive outputs. | Scheduled backups; source data reconciliation; versioned reporting templates. | 4 — Standard | Annually |  |  | Not Tested | Identify critical reporting deadlines and manual workarounds. | Validate regulatory obligations and actual reporting calendar.

## Recovery Plan
Plan ID | Scenario | Activation Criteria | Incident / Crisis Lead | Recovery Coordinator | Immediate Actions | Recovery Sequence | Communications | Dependencies / Suppliers | Return to Normal Criteria | Approval / Escalation | Related Evidence ID | Status | Notes
BCP-001 | Ransomware or destructive malware | Suspected widespread encryption, integrity loss, or compromise of critical services; follow incident command and containment procedure. | Incident Response Lead | IT Recovery Lead | Declare incident; isolate affected systems under approved procedure; preserve evidence; activate crisis roles. | 1. Assess scope and trusted backups. 2. Contain threat. 3. Rebuild clean recovery environment. 4. Restore identity and priority services. 5. Validate integrity. 6. Resume in approved order. | Use approved internal channels; designate a communications lead; coordinate customer, regulator, and supplier communications as applicable. | Identity provider; backup platform; hosting provider; security monitoring | Threat contained; clean environment validated; business owner accepts service; monitoring heightened; lessons captured. | Escalate according to incident severity matrix; only authorized leaders approve recovery and service resumption. | EVD-005; EVD-006; EVD-007 | Draft | Illustrative scenario; tailor to actual architecture and incident procedures.
BCP-002 | Cloud / hosting region outage | Critical hosted services unavailable beyond the service-specific trigger or provider declares major outage. | Crisis Manager | IT Recovery Lead | Confirm provider status; assess impact; activate continuity arrangements and supplier escalation. | 1. Confirm failure domain. 2. Validate alternate capacity. 3. Recover network and identity dependencies. 4. Restore critical services. 5. Reconcile data. 6. Validate with service owners. | Use approved status page and customer communication process; avoid unverified claims. | Cloud / hosting provider; DNS; network; identity; databases | Primary service stable or alternate service approved; data reconciled; service owner signs off; monitoring active. | Invoke supplier escalation and business continuity governance as defined by policy. | EVD-007; EVD-008; EVD-012 | Draft | Validate provider capabilities, data residency, and contractual recovery commitments.
BCP-003 | Loss of identity provider | Staff or customers cannot authenticate to critical services and approved recovery threshold is reached. | IT Operations Manager | Identity Recovery Lead | Invoke identity recovery procedure; verify incident scope; use controlled emergency access with enhanced logging. | 1. Confirm directory and MFA status. 2. Recover trusted identity components. 3. Validate privileged access. 4. Restore dependent services. 5. Review emergency access use. | Communicate through approved out-of-band channels; provide updates to service owners. | Directory; MFA; privileged access; DNS; endpoint management | Authentication stable; access tests pass; emergency credentials rotated or disabled as appropriate; logs reviewed. | Security lead and service owners approve return to normal operation. | EVD-004; EVD-007 | Draft | Never put real break-glass credentials or recovery secrets in this public workbook.
BCP-004 | Critical third-party service failure | A critical supplier outage materially affects a critical business service or exceeds agreed escalation threshold. | Third-Party Risk Manager | Service Owner | Confirm supplier incident; activate contract escalation; assess alternate/manual operating options. | 1. Assess impact. 2. Engage supplier. 3. Activate workaround or alternate supplier route if approved. 4. Reconcile transactions/data. 5. Confirm stable service. | Coordinate supplier, internal stakeholders, and customer updates through approved communications lead. | Critical ICT supplier; contractual contacts; dependent applications | Supplier service restored or approved alternative operating model stable; reconciliation complete; incident review recorded. | Escalate material risks and decisions to authorized management. | EVD-008; EVD-012 | Draft | Check exit plans and supplier contact details in a controlled location, not public GitHub.