## Summary
BalticTrust Bank — Incident Management Plan
Portfolio demonstration ¦ Fictional financial institution ¦ Review and approve before real-world use
Purpose | Provide a repeatable process to report, classify, escalate, investigate, contain, eradicate, recover from, and learn from ICT/security incidents.
Scope | Illustrative incidents affecting customer-facing banking services, identity systems, endpoints, networks, cloud/hosting, data, and ICT suppliers.
Operating principle | Protect people and customers first; preserve evidence; coordinate decisions; communicate through approved channels; document a clear timeline.
Plan owner | Head of Information Security (proposed role)
Incident coordinator | Incident Manager / SOC Lead (proposed role)
Review cadence | At least annually and after a major incident or exercise (proposed).
Important limitation | This is a fictional template. It does not establish legal compliance, reporting deadlines, or operational readiness.

## Read Me
How to Use This Workbook
Replace illustrative assumptions with approved procedures, contacts, and legal requirements.
Topic | Guidance
1. Prepare | Confirm scope, incident channels, on-call contacts, decision authority, legal/privacy contacts, and supplier escalation paths.
2. Detect and report | Record who reported the event, when it was detected, affected systems, observable indicators, and immediate safety/customer impact.
3. Classify | Use the classification matrix as a starting point. Record the rationale and escalate when severity is uncertain.
4. Coordinate | Assign an Incident Manager, open an incident record, establish a timeline, and maintain a decision/action log.
5. Contain and investigate | Use approved playbooks and authorized personnel. Preserve relevant logs and evidence; document evidence handling and access.
6. Recover | Restore from trusted sources, validate service integrity, monitor for recurrence, and obtain business-owner approval before full return.
7. Communicate | Use approved internal/external channels. Legal, privacy, regulatory and customer notifications must be assessed by qualified owners against applicable requirements.
8. Learn | Run a post-incident review, identify root causes and control gaps, assign remediation owners and due dates, and track completion.
Recordkeeping | Keep incident records, evidence references, decisions, communications, and lessons learned according to approved retention rules.
Use limitation | All roles, severity thresholds, and response targets in this workbook are proposed examples—not approved policy or evidence of compliance.

## Incident Classification
Incident Classification Matrix
Initial triage aid only; classify using business impact, data sensitivity, scope, and confidence.
Severity | Illustrative criteria | Initial handling | Notify / engage | Update approach | Notes
SEV-1 Critical | Confirmed or highly likely major disruption to a critical banking service; widespread privileged compromise; material data exfiltration; active destructive attack. | Immediate | Incident Manager + executive crisis lead + Security + IT operations + Legal/Privacy as relevant | Continuous coordination; executive updates at agreed intervals | Proposed example; validate against business impact analysis and applicable rules.
SEV-2 High | Significant degradation of an important service; confirmed compromise of a sensitive account/system; limited but material data exposure. | Urgent | Incident Manager + Security lead + affected service owner | Frequent updates based on impact and duration | Proposed example; raise to SEV-1 if impact expands.
SEV-3 Medium | Contained malware, suspicious activity with credible indicators, or localized service disruption with limited impact. | Prompt | Security/SOC lead + system owner | Updates at key investigation milestones | Escalate if scope, persistence, or customer impact increases.
SEV-4 Low | Low-confidence alert or isolated policy/security event with no current evidence of compromise or service impact. | Routine | SOC/IT support; consult Security as needed | Document disposition and monitoring decision | Do not close solely because initial evidence is limited.

## Response Roles
Incident Response Roles and Responsibilities
Assign named people and deputies before operational use.
Role | Responsibilities | Decision authority (proposed) | Key records
Incident Manager | Coordinates response, assigns actions, maintains timeline/decision log, escalates severity. | Declare/coordinate incident response; request resources. | Incident record, action log, status updates.
Security / SOC Lead | Validates alerts, directs technical investigation, threat hunting, and evidence preservation. | Recommend containment and security actions. | Indicators, investigation notes, evidence references.
IT / Service Owner | Explains system dependencies; implements approved containment and recovery actions. | Execute changes within delegated authority. | Service impact, change records, recovery validation.
Business Continuity Lead | Assesses business impact and coordinates continuity arrangements. | Recommend business workarounds and prioritization. | Business impact and continuity decisions.
Legal / Privacy Lead | Assesses legal privilege, privacy impact, notification obligations, and regulator/customer communications. | Advise on legal/privacy decisions and required notifications. | Documented assessment and approvals.
Communications Lead | Prepares consistent internal and external messaging with authorized approvers. | Issue approved communications via agreed channels. | Message versions, approvals, recipient/audience log.
Executive Crisis Lead | Makes major risk, service, customer, and resource decisions. | Approve high-impact business decisions within authority. | Executive decisions and escalations.
Supplier Manager | Coordinates third-party incident contacts, contractual obligations, and supplier evidence. | Activate supplier escalation path. | Supplier notifications, response status, dependencies.

## Response Lifecycle
Incident Response Lifecycle
Adapt to internal procedures and incident type; not every incident follows a strictly linear sequence.
Step | Phase | Accountable roles | Core actions | Records to retain | Escalation / safeguards
1 | Report / detect | Reporter, SOC, service owner, supplier | Capture detection time, source, indicators, impacted assets, initial impact. | Incident ticket; initial evidence references | Immediately route suspected major incidents to on-call response.
2 | Triage / classify | SOC Lead + Incident Manager | Validate signal, assess impact/scope/confidence, assign provisional severity. | Severity rationale; affected services; assumptions | Escalate if critical service/customer/data impact is possible.
3 | Mobilize | Incident Manager | Assign roles, open collaboration channel, establish update cadence and action log. | Role assignments; contact log; decision log | Use approved out-of-band channels if normal systems may be compromised.
4 | Contain | Security + IT / Service Owner | Limit spread and harm using authorized, proportionate actions; consider business continuity. | Actions, approvals, timestamps, change records | Preserve evidence; assess operational consequences before disruptive actions.
5 | Investigate / eradicate | Security / SOC + specialists | Determine entry path, scope, persistence, data/service impact; remove root cause. | Timeline, indicators, evidence references, findings | Maintain evidence integrity and restrict access to sensitive material.
6 | Recover / validate | IT / Service Owner + Business Owner | Restore trusted services, validate integrity, monitor, confirm business acceptance. | Recovery checks; monitoring results; approval | Do not declare resolved until agreed exit criteria are met.
7 | Communicate / assess reporting | Legal/Privacy + Communications + Incident Manager | Assess notification obligations and prepare approved updates for relevant audiences. | Assessment, approvals, messages and timestamps | Applicable deadlines depend on jurisdiction, incident facts, and current law.
8 | Close / learn | Incident Manager + control owners | Run post-incident review; assign root-cause and control remediation actions. | Final report; lessons learned; remediation tickets | Track actions to closure and update plans/playbooks.

## Incident Register
Incident Register — Example Records
Example rows are fictional demonstrations. Replace with real records only in an authorized environment.
Incident ID | Detected date | Title | Category | Severity | Status | Affected asset/service | Reported by/team | Initial impact / observations | Immediate actions / next steps | Incident owner | Review / target date | Notes
INC-2026-001 | 2026-09-14 | Suspicious privileged login | Identity / Access | SEV-2 High | Under investigation | Identity platform | Security Operations | Unusual sign-in from unfamiliar location; no confirmed data access at triage. | Disable session, verify MFA and logs, review privileged activity. | Security Lead | 2026-09-15 | Fictional example; validate scope before final severity.
INC-2026-002 | 2026-09-22 | Ransomware alert on endpoint | Malware / Ransomware | SEV-1 Critical | Contained (example) | Employee endpoint fleet | IT Operations | EDR alert with encryption behavior; scope not yet confirmed in example. | Isolate affected endpoint(s), preserve logs, hunt for lateral movement, assess backups. | Incident Manager | 2026-09-23 | Fictional example; dates and status are illustrative.
INC-2026-003 | 2026-10-02 | Payment service availability degradation | Availability | SEV-2 High | Resolved (example) | Payment API | Payments Service Owner | Elevated error rates linked to a deployment; no evidence of malicious activity in example. | Rollback deployment, validate transactions, monitor error rate, review change controls. | Service Owner | 2026-10-03 | Fictional example; not actual BalticTrust Bank activity.

## Action and Decision Log
Action and Decision Log
Use one row per material action or decision; timestamps and approvers are important for traceability.
Incident ID | Timestamp | Type | Action / decision | Assigned to | Status | Approved by | Approval timestamp | Evidence / notes
INC-2026-001 | 2026-09-14 09:10 | Triage | Review identity provider alerts and authentication logs | Security Lead | In progress | Incident Manager | 2026-09-14 09:05 | Example only
INC-2026-002 | 2026-09-22 11:20 | Containment | Isolate suspected affected endpoint and preserve EDR telemetry | IT Operations | Completed (example) | Incident Manager | 2026-09-22 11:15 | Example only
INC-2026-003 | 2026-10-02 14:30 | Recovery | Rollback deployment and validate payment API health | Payments Service Owner | Completed (example) | Change approver | 2026-10-02 14:25 | Example only

## Post-Incident Review
Post-Incident Review Template
Complete after containment/recovery; use factual evidence and blameless analysis.
Section | Questions / expected content
Incident overview | What happened? When was it detected? Which services, data, and users were affected?
Impact assessment | Duration, customer/business impact, data sensitivity, operational consequences, and confidence in findings.
Timeline | Key events, decisions, communications, containment, recovery, and approval timestamps.
Root cause and contributing factors | Technical, process, human, supplier, and control factors supported by evidence.
What worked well | Controls, detections, communication, and response activities that reduced impact.
What needs improvement | Detection gaps, access weaknesses, process delays, unclear ownership, or recovery issues.
Remediation actions | Action ID, owner, due date, priority, dependency, and closure evidence.
Notification assessment | Document Legal/Privacy assessment, applicable requirements, decisions, approvals, and timestamps.
Approval and closure | Incident Manager and relevant service/business owner sign-off; unresolved risks and follow-up date.