## Dashboard
BalticTrust Bank — GRC Management Dashboard
Illustrative portfolio dashboard ¦ Fictional institution ¦ Update metrics from validated registers
Portfolio status |  |  | Reporting basis
Illustrative sample data |  |  | As of: 9 October 2026
Assets in inventory |  | Open risk items | High/Critical risks |  | Open remediation actions
Risk distribution |  |  | Remediation status
Risk band | Count |  | Action status | Count
Critical | 2 |  | Open | 4
High | 4 |  | In progress | 3
Moderate | 3 |  | Closed | 3
Low | 1

## Dashboard Data
Dashboard Data — Illustrative Records
Replace these examples with current, validated data from the portfolio registers. Do not treat sample figures as actual audit results.
Record ID | Record type | Description | Risk band | Owner | Risk status | Source / area | Target date | Remediation status | Evidence / notes
R-001 | Risk | Cloud provider outage | Critical | Cloud Operations | Open | Third-party risk | 2026-11-15 | Open | Fictional example
R-002 | Risk | Identity provider compromise | High | Identity Owner | Open | Third-party risk | 2026-11-20 | Open | Fictional example
R-003 | Risk | Payment processing disruption | Critical | Payments Owner | Open | Third-party risk | 2026-11-10 | In progress | Fictional example
R-004 | Risk | Sensitive security telemetry exposure | High | Security Operations | Open | Third-party risk | 2026-12-01 | In progress | Fictional example
R-005 | Risk | Incomplete asset ownership | High | IT Asset Owner | Open | Asset inventory | 2026-11-30 | Open | Fictional example
R-006 | Risk | Access review not evidenced | Moderate | IAM Owner | Open | Security controls | 2026-12-10 | In progress | Fictional example
R-007 | Risk | Backup restore not tested | Moderate | Infrastructure Lead | Open | BCP / DR | 2026-12-15 | Open | Fictional example
R-008 | Risk | Incident escalation contacts outdated | Moderate | Incident Manager | In progress | Incident management | 2026-11-25 | Closed | Fictional example
R-009 | Risk | Supplier exit plan incomplete | High | Supplier Manager | Open | Third-party risk | 2026-12-20 | In progress | Fictional example
R-010 | Risk | Policy review overdue | Low | GRC Manager | Closed | GRC gap assessment | 2026-10-20 | Closed | Fictional example

## Metric Definitions
Metric Definitions and Governance
Agree definitions before presenting metrics to management.
Metric | Meaning | Governance / maintenance
Assets in inventory | Count of populated record IDs in the Dashboard Data sample. | Replace with a linked count from the approved asset inventory.
Open risk items | Number of sample rows with risk status Open. | Use the organization's risk register and agreed status values.
High/Critical risks | Count of rows with High or Critical risk band. | Use approved risk scoring thresholds; explain material changes.
Open remediation actions | Number of sample rows with remediation status Open. | Connect to remediation tracker; distinguish overdue from open.
Risk distribution | Sample risk count by illustrative band. | A risk count alone does not show exposure or business impact.
Remediation status | Sample actions grouped by Open, In progress, and Closed. | Closure requires evidence and authorized validation.
Reporting date | Date the sample dashboard was prepared. | Update to actual reporting period when the source registers are validated.
Data quality caveat | This workbook is not automatically connected to other portfolio workbooks. | Manually reconcile figures to source registers and document refresh date.